## Status
Directory	File	Purpose	Status	Comment	Packages Installed
setup	bootstrap.sh	Run with curl, download this script, pull correct TAG# from git, start setup script	NOT DONE		git
setup	start.sh	create system startup script, define global variables, start service installation and configuration, start management daemon	IN PROGRESS
setup	functions.sh	definitions for later use	DONE
setup	preflight.sh	system sanity checks before starting	DONE
setup	randomize.sh	Seed random number generators early, allow entropy to build up so that it is large enough when needed to generate security keys	DONE
setup	py3-venv.sh	Create python3 virtual environment if it is a first-time-setup	DONE
setup	questions.sh	get input from the user, validate email address BUT installs python3 and pip3 globally	IN PROGRESS; still need to test in interactive environment, also test email_validation which uses python3	MUST create python3 virtual environment here and use it exclusively hereafter. / Installed into final location usr/local/lib/mailinabox/env/	dialog / python3 / pip3 / email_validator
setup	network-checks.sh	make sure IP address is not blacklisted and we can make outbound connection on port 25	DONE		bind-utils / nmap-ncat
setup	migrate.py	do migrations from previous versions	DONE
setup	system.sh	sanity checks and setup system wide parameters, install support packages eg. bc, git, curl, wget; setup automatic security updates	IN PROGRESS	NOT able to test timezone in Vagrant
setup	dns-local.sh	Install and configure bind (named) to listen on localhost only and use DNSSEC	DONE	etc/resolv.conf survive restarts ?? (initially auto configured by Network Manager)
setup	fail2ban.sh	Installs and configures all fail2ban filters / All jails are defined in conf/fail2ban folder	IN PROGRESS	Will revisit full fail2ban installation and config once all apps are installed and all log files exist…...maybe better to move to end of installation??
conf	fail2ban/jails.conf	Enable and define jails and which filters to use	NOT DONE	MIAB filters seem very dated. Will use default filters from CentOS installation as much as possible.
conf	fail2ban/filter.d/*	Definitions of filters	NOT DONE	Need to double check this, especially the location of log files, owncloud vs next cloud.
setup	ssl.sh	Create and self-sign initial ssl certificates	DONE
setup	dns.sh	Install and configure nsd / Create DNSSEC signing keys	DONE
setup	Mail-postfix.sh	Install and cofigure postfix	DONE	See systemctl status postfix / Unused parameter: smtp_dns_support_level=dnssec / This was introduced in v2.11, CentOS on v2.10!!! / For DANE TLS authentication in postfix see http://www.postfix.org/TLS_README.html / Installed v3.2 from IUS repositories / Fail2ban is also uninstalled…..another reason to move it to the end
tools	editconf.py	Edit config files but must use python3 from our virtual environment	DONE

management	status_checks.py			There are %d software packages that can be updated." FIX THE GRAMMAR!

## Future Ideas
Dir	file	Idea
setup	dns-local.sh	Need a test to see if etc/resolv.conf gets replaced or modified by cloud vendor.			SELinux
setup	ssl.sh	openssl genrsa has actually been superceded by openssl genpkey (openssl genpkey -algorithm RSA -pkeyopt rsa_keygen_bits:2048 -out genpkey.key)……change to this ? See https://unix.stackexchange.com/questions/415970/openssl-genpkey-algorithm-rsa-vs-genrsa			every file we created we need to reset with restore -F -r filename
management	system_checks.py	Can use this to create a check on all open firewall ports / firewall-cmd –service=dns –get-ports –permanent / Have a system check that only the “approved” ports are open and no others
setup	Mail-dovecot.sh	why is first valid user id = 0??? Ubuntu default = 500, CentOS default = 1000, comments in etc/dovecot/conf.d/10-mail.conf even say setting to 0 is useless
management	system_checks.py	When there is only one sw package to be updated, the grammar is incorrect!!!
??	??	How to know if a reboot is required? Show this in system checks / https://serverfault.com/questions/122178/how-can-i-check-from-the-command-line-if-a-reboot-is-required-on-rhel-or-centos